## Sheet1
Project Plan:	Project Name: Address Book
Task Number:	WBS Number	Task Description:					Dependencies			Who does it?		Start		End
1	1	Select Client to work with: Wolf Academy
2	1.1	Provide project Overview/Brief					SP		01.12.15		01.12.15
3	1.2	Establish Functional/Non Functional Requirements					1.1			Wolf		01.12.15		01.12.15
4	1.3	Create Design Document					1.2			Wolf/SP		01.12.15		01.12.15
5	1.4	Create Application Wireframe					1.3			SP		01.12.15		02.12.15
6	1.5	Establish Database Normalisation: Primary/Foreign Keys					1.4			SP		01.12.15		02.12.15
7	1.6	Establish Database design: Correct Data Types					1.5			SP		01.12.15		02.12.15
8	1.7	Establish Database design: use of NULL/NOT NULL					1.6			SP		01.12.15		02.12.15
9		Milestone 1 – All preliminary Documentation complete and sent to Wolf via Dropbox.
10	1.8	Install Wolf Data Objcts into Visual Studio					1.2			SP		02.12.15		02.12.15
11	1.9	Install SQL Server					1.7			SP		02.12.15		03.12.15
12	2.0	Develop Program					1.2 / 1.3			SP		02.12.15		06.12.15
13		Milestone 2 – Have Client check Application.
14	2.1	Test Plan					1.9 / 2			SP		07.12.15		08.12.15
15	2.2	Test Data					1.9 / 2			SP		07.12.15		08.12.15
16	2.3	Test Log					1.9 / 2 / 2.1 / 2.2			SP		07.12.15		08.12.15
17	2.4	Demonstrate/Send Application and Test Documents to Client					1.9 / 2 / 2.1 / 2.2 / 2.3			SP		08.12.15		08.12.15
19	2.5	Client Review					2.4			Wolf		08.12.15		08.12.15
20		Milestone 3 – Project Complete.